## Budget Template
County Opioid Board Work Plan for Opioid Funding: Example Application
Organization: Example Drug Coalition
Date: [enter submission date]
Objective What is the measurable result you are seeking to achieve? | Activities What activities will be completed that help achieve the corresponding objective? | Outcomes What measurable outcome do you hope to achieve? | Measures of Success How will the outcomes be assessed? What data points will be measured? | Timeframe When will this part of the project begin and end? | Accountability Who is responsible for each project activity? | Funds Requested What are the requested grant funds for this part of the project?
By end of fiscal year 2025, decrease recidivism rate among program participants by 25% when compared to overall justice-involved population in Cocke County. | Obtain CPRS | Establish program for justice-involved population in Cocke County | CPRS hired; Procedures in place to receive referrals from justice system | July 2024 - August 2024 | Program Director; CPRS | $55,000 for CPRS salary
same as above | Train staff to coordinate and/or carry out appropriate screenings, assessments, and support service referrals for justice-involved individuals | Screenings, assessments, and referrals are completed for each enrollment | Number of screenings, assessments, and referrals per enrollment | August 2024 - September 2024 | Program Director; Program Coordinator; CPRS | $1,000 for training materials and logistics $750 for screening and assessment materials
same as above | Provide weekly peer support counseling and recovery support services in jail and community | 100 counseling session conducted, 12 recovery meetings faciliated, and 200 support services provided | Number of counseling sessions, recovery meetings, and support services tracked as completed | August 2024 - June 2025 | CPRS | $6,250 for client vouchers $2,000 for client transportation
same as above | Meet with individuals regularly to assist in developing and maintaining a personalized plan for recovery | 25 individuals will engage in program for at least 6 months | Number of enrollments with record of engagement; duration of those enrollments | August 2024 - June 2025 | CPRS | 0
Total Funds Requested
65000